{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["영상검침시스템 설치 진행보고"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"영상검침시스템 설치 진행보고","index":0,"n_rows":13,"n_cols":10,"rows_kept":13,"cut":false,"hidden":false,"merged":[[4,1,4,5],[4,6,4,7],[4,8,4,9],[0,0,1,9],[2,1,2,5],[2,6,2,7],[2,8,2,9],[3,1,3,5],[3,6,3,7],[3,8,3,9],[6,9,7,9],[6,0,7,0],[6,1,7,1],[6,2,7,3],[6,4,7,4],[6,5,6,8],[8,2,8,3],[15,0,15,9],[16,0,16,9],[17,0,17,9],[10,2,10,3],[12,0,12,9],[13,0,13,9],[14,0,14,9],[9,2,9,3]]}
["영상검침시스템 설치 진행 보고"]
[]
["계 약 명","원격검침단말기 구입 설치",{"$nulls":4},"작 성 일",null,{"$f":"TODAY()","v":"2017-05-31"}]
["계약기간","20250314 ~ 20250910",{"$nulls":4},"장    소"]
["작업기간"," ~ ",{"$nulls":4},"설치업체"]
[]
["관리사업소","설치팀","설치기간",null,"계약수량","설치 진행 사항",null,null,null,"비고"]
[{"$nulls":5},"금일      설치수량","누적        설치수량","잔여수량","공정율"]
["김천시 상수","현경산업","20250331 ~ 20250430",null,null,null,18.0,null,"%"]
["김천시 상수","천안건축","20250331 ~ 20250430",null,null,null,0.0,null,"%"]
[null,"금일합계",null,null,{"$f":"SUM(E9:E9)","v":0},{"$f":"SUM(F9:F9)","v":0},{"$f":"SUM(G9:G9)","v":0},{"$f":"SUM(H9:H9)","v":0}]
[]
["현장 특이사항 내부보고"]